## Phase II
SN. | Main Tasks | Owner | Milestone | Start date | End Date | Status | Remarks | Links
1 | API to trigger firmware upgrade based on CI/CD build availability | Sachin | M1 |  |  | Completed
2 | Device control option per organizations | Ashutosh | M1 |  |  | Completed
3 | Combine reports for Robot and NB Test Cases | Sachin | M1 |  |  | Completed
4 | Scheduling test cases at time of Execution | Ashutosh | M1 |  |  | Completed
5 | Test group or single test case execution | Ashutosh | M1 |  |  | Completed
6 | Implementation MQTT Protocall For NB Test Case | Simpy | M1 |  |  | Completed
7 | Implementation MQTT Protocall For Robot Test Case | Sachin | M1 |  |  | Completed
8 | Testcase Import/Export Feature On List Page | Ashutosh | M1 |  |  | Completed
9 | Abort All Running and Pending NB Test Cases | Simpy | M1 |  |  | Completed
10 | Abort All Running and Pending Robot Test Cases | Simpy | M1 |  |  | Completed
11 | "Save and continue editing" should not start firmware upgrade | Ashutosh | M1 |  |  | Completed
12 | Make Firmware upgrade progress page auto-refresh | Ashutosh | M1 |  |  | Completed
13 | Start and End Time Capture on Test Executions (All Over Time , Single Time) | Sachin | M1 |  |  | Completed
14 | Manage Device specific configuration for test cases such as RPIS/PCS connected with device. | Sachin | M1 |  |  | Completed
15 | Explore Health Status Of Device | Sachin | M1 |  |  | Completed
16 | Import/export of testcase scripts For Device | Ashutosh | M1 |  |  | In Progress
17 | Import/export of testcase scripts For Robot | Sachin | M1 |  |  | In Progress
18 | MPLS KPIS Collect Through Monitoring Agent | Sachin | M1 |  |  | Pending
19 | Show All Test Cases Under The Test Category | Ashutosh | M1
1 | Expose APIs to trigger the tests from OpenWISP, so that any chatbot can trigger the required tests | Sachin | M2 |  |  | Pending
2 | 15 REST APIs to collect the test artifacts(for chatbot) | Sachin | M2 |  |  | Pending
3 | Start predefined tests based on trigger | Simpy | M2 |  |  | Pending
4 | Mail and Notification Trigger After All Test Cases are executed | Ashutosh | M2 |  |  | Pending
5 | Re-execute test cases (All ¦¦ Single) | Ashutosh | M2 |  |  | Pending
6 | Firmware Upgrade Operation Using MQTT
7